## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Prominent Programmers (Pty) Ltd | Completed | 26
Project title | Campus Coin | In Progress | 0
Stakeholder or organisation | Student Development Officer (CUT Welkom Campus) | Not Started | 0
Group mentor | Ms D Modise | Delayed | 0
Reporting phase | Unit 1 / Phase 1 | Blocked | 0
Reporting period | 1 Week | Overdue | 0
Overall status | In Progress
Overall % complete | 96.3% | Contribution Summary | Count
Main achievement | Successfully identified our Stakeholder | Contribution entries | 8
Main challenge | Finding a very convincing name of the project | Verified entries | 8
Next planned activity | More formal meetings with the stakeholder | Unverified entries | 0
|  | Stakeholder engagements | 2

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student(s) | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | Mr. Phakamile Zangwa | 2026-08-17 | 2026-08-18 | Completed | 100 |  | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | Mr. Thina Mngxozana | 2026-08-18 | 2026-08-25 | Completed | 100 |  | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | Mr. Lwazi Nkambule | 2026-08-20 | 2026-08-25 | Completed | 100 |  | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | Ms. Mamello Nthako | 2026-08-20 | 2026-08-24 | Completed | 100 |  | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | Ms. Evelyn Mokone | 2026-08-20 | 2026-08-26 | Completed | 100 |  | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | Mr. Lunga Mthokonya | 2026-08-20 | 2026-08-28 | Completed | 100 |  | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | Mr. Sibusiso Ngwenya | 2026-08-20 | 2026-08-26 | Completed | 100 |  | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | Mr. Thina Mngxozana | 2026-08-20 | 2026-08-21 | Completed | 100 |  | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | Mr. Lwazi Nkambule and Mr. Lunga Mthokonya | 2026-08-20 | 2026-08-25 | Completed | 100 |  | Yes |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | Mr. Phakamile Zangwa | 2026-08-20 | 2026-08-21 | Completed | 100 |  | Yes |  | Completed
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | Ms. Mamello Nthako and Ms. Evelyn Mokone | 2026-08-20 | 2026-08-21 | Completed | 100 |  | Yes |  | Completed
U3-01 | Phase 2 | Activity 3.1 | Identtify the main system components | Mr. Phakamile Zangwa | 2026-09-04 | 2026-09-12 | Completed | 100 |  | Yes |  | Completed
U3-02 | Phase 2 | Activity 3.1 | Identify who uses each applicatiomn | Mr. Thina Mngxozana | 2026-09-04 | 2026-09-12 | Completed | 100 |  | Yes |  | Completed
U3-03 | Phase 2 | Activity 3.1 | Identify the Responsibility of each component | Mr. Lwazi Nkambule | 2026-09-07 | 2026-09-12 | Completed | 100 |  | Yes |  | Completed
U3-04 | Phase 2 | Activity 3.1 | Identify the main data flows | Ms. Mamello Nthako | 2026-09-07 | 2026-09-12 | Completed | 100 |  | Yes |  | Completed
U3-05 | Phase 2 | Activity 3.1 | Draw the system architecture diagram | Ms. Evelyn Mokone | 2026-09-08 | 2026-09-12 | Completed | 100 |  | Yes |  | Completed
U3-06 | Phase 2 | Activity 3.2 | Develop the Use Case Diagram | Mr. Lunga Mthokonya | 2026-09-08 | 2026-09-12 | Completed | 100 |  | Yes |  | Completed
U3-07 | Phase 2 | Activity 3.2 | Develop the Sequence Diagrams | Mr. Sibusiso Ngwenya | 2026-09-08 | 2026-09-12 | Completed | 100 |  | Yes |  | Completed
U3-08 | Phase 2 | Activity 3.2 | Develop the Database Design | Ms. Dimpho Radile | 2026-09-08 | 2026-09-12 | Completed | 100 |  | Yes |  | Completed
U3-09 | Phase 2 | Activity 3.3 | Review the approved requirements | Ms. Evelyn Mokone | 2026-09-04 | 2026-09-12 | Completed | 100 |  | Yes |  | Completed
U3-10 | Phase 2 | Activity 3.3 | Identify the required flutter screens | Mr. Thina Mngxozana | 2026-09-04 | 2026-09-12 | Completed | 100 |  | Yes |  | Completed
U3-11 | Phase 2 | Activity 3.3 | Identify the required ASP.NET screens | Mr. Sibusiso Ngwenya | 2026-09-08 | 2026-09-12 | Completed | 100 |  | Yes |  | Completed
U3-12 | Phase 2 | Activity 3.3 | Create Wireframes | Ms. Dimpho Radile | 2026-09-08 | 2026-09-12 | Completed | 100 |  | Yes |  | Completed
U3-13 | Phase 2 | Activity 3.3 | Check the Mobile and Web Integration | Mr. Lwazi Nkambule | 2026-09-07 | 2026-09-12 | Completed | 100 |  | Yes |  | Completed
U3-14 | Phase 2 | Activity 3.3 | Update the system design | Mr. Lunga Mthokonya | 2026-09-08 | 2026-09-12 | Completed | 100 |  | Yes |  | Completed
U3-15 | Phase 2 | Activity 3.3 | Update Project Records | Mr. Phakamile Zangwa | 2026-09-04 | 2026-09-12 | Completed | 100 |  | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND(#REF!<>"",#REF!<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
Mr. Phakamile Zangwa | 218004524 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | Successfully engaged the stakeholder informally and formally for their involvement. | 2026-08-18 | 24 | Attached on zip folder | Yes | 2026-08-26
Mr. Thina Mngxozana | 224022878 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | All processes were documented on the SRS version 1.0 | 2026-08-25 | 27 | Attached on zip folder | Yes | 2026-08-26
Mr. Lwazi Nkambule | 223000859 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | All definitions were documented on the SRS version 1.1 | 2026-08-25 | 36 | Attached on zip folder | Yes | 2026-08-26
Ms. Mamello Nthako | 222031189 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | All question were prepared on time and the group reharsed them when approaching the stakeholder. | 2026-08-24 | 12 | Attached on zip folder | Yes | 2026-08-26
Ms. Evelyn Mokone | 221025681 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | Both the informal and formal meetings were conducted under my guidence | 2026-08-26 | 128 | Attached on zip folder | Yes | 2026-08-26
Mr. Lunga Mthokonya | 221038861 | Unit 1 / Phase 1 | Activity 1.2 | Compile the initial SRS | I compliled the first version of the SRS | 2026-08-20 | 15 | Attached on zip folder | Yes | 2026-08-26
Mr. Sibusiso Ngwenya | 223045887 | Unit 1 / Phase 1 | Activity 1.2 | Create the initial Microsoft Project schedule | I created the Microsoft Project Schedule and gave all my colleagues roles and responsebilities | 2026-08-26 | 20 | Attached on zip folder | Yes | 2026-08-26
Ms. Dimpho Radile | 219008387 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | I helped to have an overview of the progress made by the group. Also assessed the progress made vs the roles assigned | 2026-08-31 | 12 | Final Documents Attached on the zip folder | Yes | 2026-08-31

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
2026-08-17 | Unit 1 / Phase 1 | Other | Informal Meeting | Mr. Phakamile Zangwa, Ms. Evelyn Mokone, Ms. Mamello Nthako | Mrs. Henson Maggie - CUT Student Development Officer | 1. Confirmed poor attendance on SDO and other departmental and structures event | Brainstorm and document down all tasks and roles expected
2026-08-26 | Unit 1 / Phase 1 | Meeting | Formal Meeting | Mr. Phakamile Zangwa, Ms. Evelyn Mokone, Ms. Mamello Nthako & Mr Lunga Mthokonya | Mrs. Henson Maggie - CUT Student Development Officer | Stakeholder Conformation Letter | Start Phase 2 of the Project

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 1 / Phase 1 | Initial or updated SRS completed | Yes
Reporting period | 2026-08-31 | Progress report updated | Yes
Overall phase status | Completed | Individual contributions recorded | Yes
What was completed during this phase? | Planning and documenting everything required for the Phase 2. Especially identifying the problem. | Stakeholder engagement recorded | Yes
What remains incomplete? | None | Challenges and actions updated | Yes
Why is it incomplete? | Everything | Group reflection completed | Yes
Which contributions were particularly important? | All contributions of team members played a key role. Especially when we got the 8th member to verify all progress made and acuuracy of our documentation. | Microsoft Project updated | Yes
Were there participation concerns? | None. Everyone played their part and apologies were sent on time. | GitHub evidence available | Yes
What will the group improve in the next phase? | For Phase 2: We want to prioratise immediate execution of tasks - we do not want to work under-pressure. Our stakeholder has urged for the prototype as soon as possible. | Confidential peer check completed | Yes
Main priority for the next phase | Completing Phase 2 before the deadline. This will require tasks to be shared by members.

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 1 / Phase 1 | Length | Approximately 300–400 words in total.
Project title | Campus Coupon | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | Planning is imperative in assisting what to do next, everything written can be useful when executing. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | Documenting the Phase 1 project was a success because of teamwork and delegating responsebilities | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | Deciding to continue or drop off the Lost and Found system on our Campus Coupon project. We really see a high need of ensuring that this project assists with students participation and networking. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Each member volunteered their services based on their strengths. The remaining responsebilities were assigned to two or more members for completion.
Did all members contribute fairly? Explain. | Yes - all members were hands-on. Especially when having late night calls reminding each other to meet the deadlines.
How did the group handle disagreements or delays? | Most of disagreements were subjected to votes. So we all agreed that the majority will decide and we shall implement what the majority has decided.
What did the group learn from the stakeholder? | The stakeholder requested for the complience with the POPIA Act and further urged Prominent Programmers (Pty) Ltd to commit themselves to not to misuse the information of all users.
Improvement action 1 for the next phase | For the next phase - we believe it would be best to pair responsebilities. Most of tasks that were assigned to 2 people were completed before deadline.
Improvement action 2 for the next phase | We should improve on communication - we believe the group must communicate more. Also we should keep each other posted on all kinds of progress.
Priority for the next phase | For Phase 2: We want to prioratise immediate execution of tasks - we do not want to work under-pressure. Our stakeholder has urged for the prototype