## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Prominent Programmers (Pty) Ltd | Completed | 30
Project title | Campus Coupon | In Progress | 0
Stakeholder or organisation | Student Development Officer (CUT Welkom Campus) | Not Started | 0
Group mentor | Ms D Modise | Delayed | 0
Reporting phase | Unit 3 / Phase 2 | Blocked | 0
Reporting period | 8–30 September 2026 | Overdue | 0
Overall status | Completed
Overall % complete | 96.77% | Contribution Summary | Count
Main achievement | Completed the Phase 2 system design deliverables: architecture, UML, ERD, Flutter and ASP.NET interface designs, design-source links, stakeholder review and project records. | Contribution entries | 24
Main challenge | Maintaining consistency across the architecture, UML, database design and interfaces required repeated review and alignment. The design was updated following stakeholder/lecturer guidance. | Verified entries | 24
Next planned activity | Begin Phase 3 development, integration and testing. | Unverified entries | 0
|  | Stakeholder engagements | 4

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student(s) | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | Mr. Phakamile Zangwa | 2026-08-17 | 2026-08-18 | Completed | 100 |  | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | Mr. Thina Mngxozana | 2026-08-18 | 2026-08-25 | Completed | 100 |  | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | Mr. Lwazi Nkambule | 2026-08-20 | 2026-08-25 | Completed | 100 |  | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | Ms. Mamello Nthako | 2026-08-20 | 2026-08-24 | Completed | 100 |  | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | Ms. Evelyn Mokone | 2026-08-20 | 2026-08-26 | Completed | 100 |  | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | Mr. Lunga Mthokonya | 2026-08-20 | 2026-08-28 | Completed | 100 |  | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | Mr. Sibusiso Ngwenya | 2026-08-20 | 2026-08-26 | Completed | 100 |  | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | Mr. Thina Mngxozana | 2026-08-20 | 2026-08-21 | Completed | 100 |  | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | Mr. Lwazi Nkambule and Mr. Lunga Mthokonya | 2026-08-20 | 2026-08-25 | Completed | 100 |  | Yes |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | Mr. Phakamile Zangwa | 2026-08-20 | 2026-08-21 | Completed | 100 |  | Yes |  | Completed
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | Ms. Mamello Nthako and Ms. Evelyn Mokone | 2026-08-20 | 2026-08-21 | Completed | 100 |  | Yes |  | Completed
U3-01 | Phase 2 | Activity 3.1 | Identify the main system components | Mr. Phakamile Zangwa | 2026-09-08 | 2026-09-25 | Completed | 100 | Final SRS – Activity 3.1 architecture section | Yes |  | Completed
U3-02 | Phase 2 | Activity 3.1 | Identify who uses each application | Mr. Thina Mngxozana | 2026-09-08 | 2026-09-25 | Completed | 100 | Final SRS – Activity 3.1 component/user responsibilities | Yes |  | Completed
U3-03 | Phase 2 | Activity 3.1 | Identify the responsibility of each component | Mr. Lwazi Nkambule | 2026-09-08 | 2026-09-25 | Completed | 100 | Final SRS – Activity 3.1 component responsibilities | Yes |  | Completed
U3-04 | Phase 2 | Activity 3.1 | Identify the main data flows | Ms. Mamello Nthako | 2026-09-08 | 2026-09-25 | Completed | 100 | Final SRS – Activity 3.1 data-flow section | Yes |  | Completed
U3-05 | Phase 2 | Activity 3.1 | Draw the system architecture diagram | Ms. Evelyn Mokone | 2026-09-08 | 2026-09-25 | Completed | 100 | Final SRS – architecture diagram; editable source identified in SRS | Yes |  | Completed
U3-06 | Phase 2 | Activity 3.2 | Develop the Use Case Diagram | Mr. Lunga Mthokonya | 2026-09-08 | 2026-09-25 | Completed | 100 | Final SRS – Use Case Diagram; editable source identified in SRS | Yes |  | Completed
U3-07 | Phase 2 | Activity 3.2 | Develop the Sequence Diagrams | Mr. Sibusiso Ngwenya | 2026-09-08 | 2026-09-25 | Completed | 100 | Final SRS – Sequence Diagrams; editable sources identified in SRS | Yes |  | Completed
U3-08 | Phase 2 | Activity 3.2 | Develop the Database Design | Ms. Dimpho Radile | 2026-09-08 | 2026-09-25 | Completed | 100 | Final SRS – ERD/database design; editable source identified in SRS | Yes |  | Completed
U3-09 | Phase 2 | Activity 3.3 | Review the approved requirements | Ms. Evelyn Mokone | 2026-09-08 | 2026-09-25 | Completed | 100 | Final SRS – approved requirements reviewed against design | Yes |  | Completed
U3-10 | Phase 2 | Activity 3.3 | Identify the required Flutter screens | Mr. Thina Mngxozana | 2026-09-08 | 2026-09-25 | Completed | 100 | Flutter Figma prototype: https://www.figma.com/proto/BPfgfExMMI5DTg5znh0one/Untitled?node-id=0-1&t=REZsjpxCjR75XKof-1 | Yes |  | Completed
U3-11 | Phase 2 | Activity 3.3 | Identify the required ASP.NET screens | Mr. Sibusiso Ngwenya | 2026-09-08 | 2026-09-25 | Completed | 100 | ASP.NET Figma design: https://www.figma.com/design/2WycDSznQHqRO680lFkjFh/Campus-Coupon?node-id=0-1&m=dev&t=7KRC3alCJkwZbAUD-1 | Yes |  | Completed
U3-12 | Phase 2 | Activity 3.3 | Create Wireframes | Ms. Dimpho Radile | 2026-09-08 | 2026-09-25 | Completed | 100 | Flutter and ASP.NET Figma wireframes; final SRS interface section | Yes |  | Completed
U3-13 | Phase 2 | Activity 3.3 | Check the mobile and web integration | Mr. Lwazi Nkambule | 2026-09-08 | 2026-09-25 | Completed | 100 | Final SRS – integration/alignment review | Yes |  | Completed
U3-14 | Phase 2 | Activity 3.3 | Update the system design | Mr. Lunga Mthokonya | 2026-09-08 | 2026-09-25 | Completed | 100 | Final SRS – updated system design and corrected terminology | Yes |  | Completed
U3-15 | Phase 2 | Activity 3.3 | Update Project Records | Mr. Phakamile Zangwa | 2026-09-08 | 2026-09-25 | Completed | 100 | Updated SRS, Project Progress Tracker and supporting project records | Yes |  | Completed
U4-16 | Phase 3 | Activity 4.1 | Set up and Implement the shared Supabase Backend | Mr. Lunga Mthokonya & Mrs Dimpho Radile | 2026-09-10 | 2026-09-16 | Completed | 100 | Final SRS _Activity 4.1 The shared Supabase Backend has been set up and Implimented | Yes |  | Completed
U4-17 | Phase3 | Activity 4.2 | Develop Mobile Flutter Application | Mr. Lwazi Nkambule & Mr Sibusiso Ngwenya | 2026-10-09 | 2026-10-18 | Completed | 100 | Final SRS _Activity 4.2 The Mobile Flutter Application Developed | Yes |  | Completed
U4-18 | Phase3 | Activity 4.3 | Develop ASP.NET web Application | Mr Thina Mngxozana & Ms Evelyn Mokone | 2026-10-09 | 2026-10-21 | Completed | 100 | Final SRS _Activity 4.3 Developed ASP.NET web Application | Yes |  | Completed
U4-19 | Phase3 | Activity 4.4 | Integrade the Mobile and Web Application | Mr Phakamile Zangwa & Ms Mamello Nthako | 2026-10-21 | 2026-10-24 | Completed | 100 | Final SRS _Activity 4.4 Integradeed ASP.NET web Application | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
Mr. Phakamile Zangwa | 218004524 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | Successfully engaged the stakeholder informally and formally for their involvement. | 2026-08-18 | 24 | Attached on zip folder | Yes | 2026-08-26
Mr. Thina Mngxozana | 224022878 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | All processes were documented on the SRS version 1.0 | 2026-08-25 | 27 | Attached on zip folder | Yes | 2026-08-26
Mr. Lwazi Nkambule | 223000859 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | All definitions were documented on the SRS version 1.1 | 2026-08-25 | 36 | Attached on zip folder | Yes | 2026-08-26
Ms. Mamello Nthako | 222031189 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | All question were prepared on time and the group reharsed them when approaching the stakeholder. | 2026-08-24 | 12 | Attached on zip folder | Yes | 2026-08-26
Ms. Evelyn Mokone | 221025681 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | Both the informal and formal meetings were conducted under my guidence | 2026-08-26 | 128 | Attached on zip folder | Yes | 2026-08-26
Mr. Lunga Mthokonya | 221038861 | Unit 1 / Phase 1 | Activity 1.2 | Compile the initial SRS | I compliled the first version of the SRS | 2026-08-20 | 15 | Attached on zip folder | Yes | 2026-08-26
Mr. Sibusiso Ngwenya | 223045887 | Unit 1 / Phase 1 | Activity 1.2 | Create the initial Microsoft Project schedule | I created the Microsoft Project Schedule and gave all my colleagues roles and responsebilities | 2026-08-26 | 20 | Attached on zip folder | Yes | 2026-08-26
Ms. Dimpho Radile | 219008387 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | I helped to have an overview of the progress made by the group. Also assessed the progress made vs the roles assigned | 2026-08-31 | 12 | Final Documents Attached on the zip folder | Yes | 2026-08-31
Mr Phakamile Zangwa | 218004524 | Unit 3 / Phase 2 | Activity 3.1 | Identtify the main system components | I identified and documented the main system components, including the Flutter mobile application, ASP.NET web application and Supabase backend, and contributed to confirming how the components work together. | 2026-09-25 | 48 | Attached on zip folder | Yes | 2026-09-18
Mr Thina Mngxozana | 224022878 | Unit 3 / Phase 2 | Activity 3.1 | Identify who uses each applicatiomn | I identified the users of each application and documented which user interacts with the Flutter mobile application and which user interacts with the ASP.NET web application. | 2026-09-25 | 48 | Attached on zip folder | Yes | 2026-09-18
Mr Lwazi Nkambule | 223000859 | Unit 3 / Phase 2 | Activity 3.1 | Identify the Responsibility of each component | I documented the responsibilities of each system component and clarified how the Flutter application, ASP.NET application and Supabase backend support the required system functions. | 2026-09-25 | 72 | Attached on zip folder | Yes | 2026-09-18
Ms Mamello Nthako | 222031189 | Unit 3 / Phase 2 | Activity 3.1 | Identify the main data flows | I identified and documented the main data flows between the mobile application, web application and Supabase database to ensure that information is transferred correctly across the system. | 2026-09-25 | 72 | Attached on zip folder | Yes | 2026-09-18
Ms Evelyn Mokone | 221025681 | Unit 3 / Phase 2 | Activity 3.1 | Draw the system architecture diagram | I developed the system architecture diagram showing the proposed architecture | 2026-09-25 | 48 | Attached on zip folder | Yes | 2026-09-18
Mr Lunga Mthokonya | 221038861 | Unit 3 / Phase 2 | Activity 3.2 | Develop the Use Case Diagram | I developed the Use Case Diagram by identifying the relevant actors,use cases and relationships | 2026-09-25 | 72 | Attached on zip folder | Yes | 2026-09-18
Mr Sibusiso Ngwenya | 223045887 | Unit 3 / Phase 2 | Activity 3.2 | Develop the Sequence Diagrams | I developed the Sequence Diagrams to illustrate the interaction between the users, applications and backend during the key system processes. | 2026-09-25 | 72 | Attached on zip folder | Yes | 2026-09-18
Ms Dimpho Radile | 219008387 | Unit 3 / Phase 2 | Activity 3.2 | Develop the Database Design | I developed the database design by identifying the required entities, attributes, primary keys, foreign keys and relationships needed to support the system requirements. | 2026-09-25 | 72 | Attached on zip folder | Yes | 2026-09-18
Ms Evelyn Mokone | 221025681 | Unit 3 / Phase 2 | Activity 3.3 | Review the approved requirements | I reviewed the approved functional and non-functional requirements | 2026-09-25 | 72 | Attached on zip folder | Yes | 2026-09-18
Mr Thina Mngxozana | 224022878 | Unit 3 / Phase 2 | Activity 3.3 | Identify the required flutter screens | I identified the required Flutter mobile screens and documented the screens and functions needed for the student mobile experience. | 2026-09-25 | 96 | Attached on zip folder | Yes | 2026-09-18
Mr Sibusiso Ngwenya | 223045887 | Unit 3 / Phase 2 | Activity 3.3 | Identify the required ASP.NET screens | I identified the required ASP.NET web screens and documented the screens and functions needed for the administrator web experience | 2026-09-25 | 72 | Attached on zip folder | Yes | 2026-09-18
Ms Dimpho Radile | 219008387 | Unit 3 / Phase 2 | Activity 3.3 | Create Wireframes | I created the wireframes for the required mobile and web interfaces, ensuring that the screens, navigation and interface elements reflected the approved requirements. | 2026-09-25 | 96 | Attached on zip folder | Yes | 2026-09-18
Mr Lwazi Nkambule | 223000859 | Unit 3 / Phase 2 | Activity 3.3 | Check the Mobile and Web Integration | I checked the integration between the mobile and web interfaces to ensure that the proposed design supports consistent data flow and system interaction. | 2026-09-25 | 72 | Attached on zip folder | Yes | 2026-09-18
Mr Lunga Mthokonya | 221038861 | Unit 3 / Phase 2 | Activity 3.3 | Update the system design | I updated the system design based on the completed design activities and feedback, ensuring that the diagrams, interfaces and other design artefacts remained consistent with the approved requirements. | 2026-09-25 | 48 | Attached on zip folder | Yes | 2026-09-18
Mr Phakamile Zangwa | 218004524 | Unit 3 / Phase 2 | Activity 3.3 | Update Project Records | I updated and maintained the project records for Phase 2, including recording completed design activities, contributions, supporting evidence and progress against the assigned responsibilities. | 2026-09-25 | 96 | Attached on zip folder | Yes | 2026-09-18
Ms Mamello Nthako | 222031189 | Phase 3 | Activity 4,1 | Update Progress of the Project |  | 2026-10-20 | 4hours |  | Yes | 2026-10-23

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
2026-08-17 | Unit 1 / Phase 1 | Other | Informal Meeting | Mr. Phakamile Zangwa, Ms. Evelyn Mokone, Ms. Mamello Nthako | Mrs. Henson Maggie - CUT Student Development Officer | 1. Confirmed poor attendance on SDO and other departmental and structures event | Brainstorm and document down all tasks and roles expected
2026-08-26 | Unit 1 / Phase 1 | Meeting | Formal Meeting | Mr. Phakamile Zangwa, Ms. Evelyn Mokone, Ms. Mamello Nthako & Mr Lunga Mthokonya | Mrs. Henson Maggie - CUT Student Development Officer | Stakeholder Conformation Letter | Start Phase 2 of the Project
2026-09-18 | Phase 2 | Meeting | Formal Meeting | Mr Phakamile Zangwa, Ms Evelyn Mokone, Ms Mamello Nthako, Ms Dimpho Radile & Mr Sibusiso Ngwenya | Mrs. Henson Maggie - CUT Student Development Officer | Stakeholder approved the prototype & diagram | Start Phase 3 of the Project | Formal meeting minutes and meeting evidence in submission ZIP
2026-10-23 | Phase 3 | Meeting | Formal Meeting | Mr Phakamile Zangwa, Ms Evelyn Mokone, Ms Mamello Nthako, Ms Dimpho Radile & Mr Sibusiso Ngwenya, Mr Thina Mngxozana | Mr Sabata Tau-(Standing for Mrs Henson) | Stakeholder Approval for Phase 3 Working Application | Stakeholder is happy with the Project Progress | Pictures taken with Mr Tau as evidence

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 3 / Phase 2 | Initial or updated SRS completed | Yes
Reporting period | 25 September 2026 | Progress report updated | Yes
Overall phase status | Completed | Individual contributions recorded | Yes
What was completed during this phase? | Architecture, UML, ERD, Flutter and ASP.NET interface designs, integration/alignment checks, source-link documentation, stakeholder review and project records were completed. | Stakeholder engagement recorded | Yes
What remains incomplete? | No major Phase 2 design deliverable remains incomplete. The Phase 2 presentation/defence is a scheduled assessment activity, and Phase 3 development/testing follows next. | Challenges and actions updated | Yes
Why is it incomplete? | Not applicable to the completed Phase 2 design deliverables. | Group reflection completed | Yes
Which contributions were particularly important? | Architecture, UML/ERD, interface design, integration/alignment review and project documentation were key contributions. | Microsoft Project updated | Yes
Were there participation concerns? | No participation concerns recorded in the tracker. | GitHub evidence available | Yes
What will the group improve in the next phase? | Keep the documentation consistent with the approved Flutter + ASP.NET + Supabase architecture and maintain regular cross-checks during Phase 3. | Confidential peer check completed | Yes
Main priority for the next phase | Begin Phase 3 development, integration and testing.

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 3 / Phase 2 | Length | Approximately 300–400 words in total.
Project title | Campus Coupon | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | We learned how to turn approved requirements into a clear, connected system design across architecture, UML, database design and interfaces. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | Each team member had a clearly assigned responsibility, and the assigned Phase 2 design work was completed by the agreed deadline. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | Maintaining consistency across diagrams and interfaces was challenging, so we reviewed the artefacts together and adjusted them where necessary. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Tasks were divided by activity, with each member responsible for specific deliverables.
Did all members contribute fairly? Explain. | Yes. The contribution records show that members completed their assigned tasks.
How did the group handle disagreements or delays? | We discussed issues as a team, reviewed changes and adjusted the work where needed.
What did the group learn from the stakeholder? | The stakeholder approved the prototype and diagrams, confirming that the design was aligned with the project direction.
Improvement action 1 for the next phase | Improve time management by setting internal deadlines, reviewing progress regularly and addressing delays or design disagreements early.
Improvement action 2 for the next phase | Review completed work, identify challenges early and ensure that the different system components remain consistent and integrated.
Priority for the next phase | Successful implementation and integration of the Campus Coupon system, with a strong focus on functionality and testing.